2010 Korea-Bulgaria ITCC Annual Plan and Budget

November 2010

# Korea-Bulgaria IT Cooperation Center

# Contents

- History of ITCC ∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙ 3

- Briefing of ITCC ∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙3

- 2010 Action Plan ∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙4

- ITCC Operation ∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙5

- Budget ∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙∙7

# I. History of ITCC

- September 2010  MOU between MOPAS (Korea) – MTITC (Bulgaria) on Cooperation in the Area of Information Society

- September 2010  Collaboration Agreement between NIA and Sofia University for the Establishment and Operation of the ITCC

- October 2010  Dispatch Korean Coordinator of ITCC

# II. Briefing of ITCC

# 1. Framework

- The mission of ITCC is to promote sustainable collaboration in the field of ICT between Bulgaria and Korea

-  The Korean government (MOPAS) and Bulgarian government (MTITC) jointly established and will jointly supervise the center

-  NIA of Korea and Sofia University are designated as an implementing agency/organization for the operation of the ITCC

- The Korean side will contribute to cover the costs associated with the joint programs, electronic equipment and the designated dispatched personnel

- The Bulgarian side will contribute to cover the costs associated with facilities and maintenance, basic equipments, operation cost and the staffs assigned from the Bulgarian side

- The ITCC will operate from October 2010 to December 2012

# 2. Activities

[2010]

Development of ITCC Activity Roadmap

- Comprehensive review of Bulgarian e-Government status

- Development of KPI for Bulgarian e-Government development

- Sharing experiences between the two countries

- ITCC establishment and opening ceremony

[2011]

- Implementation of ITCC projects based on the Roadmap

- Adjustment and expansion of ITCC projects

[2012]

# Wrapping up of ITCC projects

- Final report will be prepared and written on ITCC activities

# III. 2010 Action Plan

# A. Organized an “Advisory Board” for joint project development

- The roles and functions of the Advisory Board

- Proposing ideas for possible projects of ITCC

- Discuss and suggest future policy/strategy of ITCC

  - Membership:

-  Government side

Mr. Valery Borissov, Director, eGovernance, MTITC

Mr. Ivan Kostov, Chairman of Foundation eHealth Care Bulgaria

-  IT Company side

Mr. Stoyan Boev, Vice President, Bulgarian IT association - BAIT

Mr. Vladimir Alexiev, Representative of IT Cluster Bulgaria and

of Bulgarian Association of Software Companies – BASSCOM

-  University side

Assoc. Prof. Dimiter Birov, Vice Dean of FMI, Sofia University,

Mr. Bojil Dobrev, Director, Sofia University Advisory & Financial Support Unit on project development and maintenance

# B. Joint Projects in 2010

- Development of ITCC Activity Roadmap up to the end of 2012

- Development of activity roadmap based on the analysis of the current status of Bulgarian Informatization including both current policies and projects

- Comprehensive Review of Bulgarian e-Government

- Development of ITCC roadmap and joint project requires an exact analysis of Bulgarian e-Government status, therefore a comprehensive review of Bulgarian e-Government will be pursued

- Period: November - December 2010

- Development of  Evaluation Tool (KPI) for Bulgaria e-Government development

- Bulgaria has invested significant amount of money for e-Gov development last several years but the result is not satisfied, therefore for the efficiency and effectiveness of Bulgaria e-Government development, Evaluation Tool (KPI) will be developed

- Period: Nov-Dec 2010

- Sharing the experiences between the two countries on Information Society development and e-Government

- Holding a workshop or seminar in order to share IT policy and projects between Korea and Bulgaria for a better understanding of both countries’ informatization policies and practices

- Period: November - December 2010

# IV. ITCC Operation

# A. Steering Committee

[1st Meeting]

- Date: Dec. 2010

- Method: Documentary Agreement

- Steering Committee Members:

Bulgaria

-	Vladimir Makariev, Director, Ministry of Transport, Information

Technology and Communications (Bulgaria, Co-chair)

-	Dimitar Tsvetkov, State Expert, Ministry of Education, Youth

and Science

-	Ivan Ilchev, Rector, Sofia University

Korea

-	Shim, Deok Seob, Director General, Ministry of Public Administration and Security (Korea, Co-chair)

-	Lee Seok Joo, Counselor, Embassy of the Republic of Korea in Bulgaria

- Park, Won Geun, Vice President for Global Cooperation Division, National Information Society Agency (NIA)

- Agenda

- Appointment of the General Director of ITCC

- Approval of the 2010 Annual Plan and Budget

[2nd Meeting]

- January 2010

- Agenda: 2011 Annual Plan and Budget

# B. Office Set-up and Opening Ceremony

- Office location: MTITC building, 1000 Sofia, Bulgaria

- Facilities

- 4 desks, 1 round table, 1 sofa, 1 refrigerator, coffee set etc…

- Interior

- Opening Ceremony

- Date: November 2010

- Details: To be determined